PRINCE2 Foundation Module 10 Quiz – Controlling a Stage

- What is the primary purpose of the Controlling a Stage process in PRINCE2?

  - To assign work, monitor such work, handle issues, report progress to the project board, and take corrective actions

  - To create detailed project plans

  - To manage stakeholder expectations

  - To close the project and hand over deliverables

- Which aspect of project management does the Controlling a Stage process NOT directly address?

  - Work assignment

  - Progress monitoring

  - Issue handling

  - Resource hiring

- How does the Controlling a Stage process contribute to project governance?

  - By ensuring the stage remains within tolerances set by the project board

  - By replacing the need for a project board

  - By automating all decision-making processes

  - By eliminating the need for stage boundaries

- In the context of Controlling a Stage, what does "taking corrective actions" primarily aim to achieve?

  - Punish team members for poor performance

  - Ensure the stage remains within set tolerances

  - Extend project timelines indefinitely

  - Increase project budget

- How does the Controlling a Stage process relate to the principle of "Manage by Exception"?

  - It contradicts this principle entirely

  - It implements this principle at the stage level

  - It only applies this principle to financial matters

  - It replaces this principle with continuous oversight

- Which of the following is NOT an objective of the Controlling a Stage process?

  - Ensure attention is focused on delivery of the stage's products

  - Ensure risks and issues are controlled

  - Ensure the business case is kept under review

  - Ensure all project documentation is updated daily

- How does the Controlling a Stage process aim to handle movement away from agreed products?

  - By encouraging such movement to promote innovation

  - By ignoring minor deviations from the plan

  - By monitoring to avoid uncontrolled change

  - By immediately halting the project

- What is the objective of the Controlling a Stage process regarding the project management team?

  - To increase the size of the team

  - To focus the team on delivery within established tolerances

  - To reduce the team's workload

  - To eliminate the need for team meetings

- How does the Controlling a Stage process aim to handle quality expectations?

  - By lowering them to ensure project completion

  - By ignoring them in favor of speed

  - By ensuring agreed products meet agreed quality expectations

  - By leaving quality concerns to the closing stage

- What is the objective of the Controlling a Stage process regarding product acceptance?

  - To delay acceptance until the end of the project

  - To ensure agreed products are accepted

  - To bypass acceptance procedures for speed

  - To outsource all acceptance activities

- When in the project lifecycle does the Controlling a Stage process typically first occur?

  - During the initiation stage

  - After the project board authorises the project

  - Only in the final stage of the project

  - Before the Starting Up a Project process

- What is the relationship between Controlling a Stage and Managing a Stage Boundary?

  - They are the same process

  - Controlling a Stage occurs throughout the stage, while Managing a Stage Boundary occurs towards the end

  - Managing a Stage Boundary replaces Controlling a Stage

  - Controlling a Stage only occurs after Managing a Stage Boundary

- How does the project manager interact with team managers during Controlling a Stage?

  - Through informal conversations only

  - By using Work Package descriptions to define, assign, and control work

  - By bypassing team managers and directly managing team members

  - Through weekly status meetings only

- What happens if the project manager is fulfilling the team manager role?

  - The Controlling a Stage process is skipped

  - Work Package descriptions are not used

  - Work Package descriptions should still be used to define and control work

  - The project board takes over all team management responsibilities

- Which of the following is NOT part of the day-to-day control cycle in Controlling a Stage?

  - Authorising work

  - Monitoring progress information

  - Reviewing the situation and triggering new work packages

  - Redefining the project's objectives

- Which of the following is NOT one of the main activities in the Controlling a Stage process?

  - Authorise a Work Package

  - Review Work Package status

  - Receive completed Work Package

  - Create the Project Initiation Documentation

- What is the purpose of the "Capture and examine issues and risks" activity?

  - To ignore all issues and risks for the sake of progress

  - To identify and evaluate problems, changes, and queries that might affect the stage objectives

  - To automatically escalate all issues to the project board

  - To create more work for the project team

- In the "Report highlights" activity, who is the primary recipient of the information?

  - The team managers

  - The project board

  - The end users

  - The suppliers

- What is the main purpose of the "Take corrective action" activity?

  - To punish team members for poor performance

  - To ensure the stage plan remains within tolerances

  - To automatically extend stage duration

  - To reduce project scope without authorisation

- When does the "Escalate issues and risks" activity occur?

  - At regular intervals regardless of the situation

  - Only at the end of the stage

  - When stage tolerances are forecast to be exceeded

  - For every minor issue encountered